## Project Timeline
The_Gruners PROJECT TIMELINE
| ENTER START DATE: | 2014-05-09
Id | ACTIVITY | START | END | NOTES
1 | Project Start | 2014-05-09 | 2014-05-09 | Start Date of Project
2 | Client Meeeting 1 | 2014-05-13 | 2014-05-13
3 | Requirement Integration | 2014-05-20 | 2014-05-23
4 | Project Timeline Compilation | 2014-05-22 | 2014-05-27
5 | First Demo Session | 2014-05-26 | 2014-05-26
6 | Requirement Re-do | 2014-05-26 | 2014-06-27
7 | System Prototype & DB Design | 2014-05-28 | 2014-06-11
8 | Progress Report 1 | 2014-05-30 | 2014-05-30
9 | Meet Stacey 1 | 2014-06-06 | 2014-06-06
10 | Client Meeeting 2 | 2014-06-20 | 2014-06-20
11 | Meet Stacey 2 | 2014-07-04 | 2014-07-04
12 | Client Meeting 3 | 2014-07-04 | 2014-07-04
13 | Critical Use Case Implementation | 2014-07-07 | 2014-07-14
14 | Progress Report 2 | 2014-07-18 | 2014-07-18
15 | Important Use Case Implementation | 2014-07-19 | 2014-07-29
16 | Second Demo Session | 2014-07-21 | 2014-07-25
17 | Meet Stacey 3 | 2014-08-01 | 2014-08-01
18 | Nice To Have Use Case Implementation | 2014-08-02 | 2014-08-16
17 | Client Meeting 4 | 2014-08-03 | 2014-08-03
18 | Progress Report 3 | 2014-08-16 | 2014-08-16
18 | Client Meeting 5 | 2014-08-17 | 2014-08-17
19 | Client Meeting 6 | 2014-08-30 | 2014-08-30
19 | Progress Report 4 | 2014-08-31 | 2014-08-31
20 | Meet Stacey 7 | 2014-09-13 | 2014-09-13
20 | Client Meeting 7 | 2014-09-13 | 2014-09-13
21 | Progress Report 5 | 2014-09-14 | 2014-09-14
22 | Client Meeting 7 | 2014-09-27 | 2014-09-27
23 | Progress Report 6 | 2014-09-28 | 2014-09-28
22 | Meet Stacy 8 | 2014-10-11 | 2014-10-11
23 | Project End | 2014-10-20 | 2014-10-20 | End Date of Project
Formulas:
START = [START, row above]+4
START = [START, row above]
END = Activities[[#This Row],[START]]
END = [START]+3

## calcs (hidden)
*** This sheet should remain hidden ***
|  | Today: | 2014-05-27
5
#N/A
#N/A
#N/A
|  | Window Activities: | 9 | #N/A
|  |  | 9 | #N/A
|  |  | 0 | #N/A
#N/A
#N/A
#N/A
|  |  |  | 1 | 1
|  |  |  | 2 | 2
|  |  |  | 3 | 3
|  |  |  | 4 | 4
|  |  |  | 5 | 5
|  |  |  | 6 | 6
|  |  |  | 7 | 7
|  |  |  | 8 | 8
|  |  |  | 9 | 9
|  | Calc Window Start | 2014-05-09
|  | Offset | 0
|  | Start | 2014-05-09
|  | Window | 30
Position | Series | Activity Id | Activity | 2014-05-09 | 2014-05-10 | 2014-05-11 | 2014-05-12 | 2014-05-13 | 2014-05-14 | 2014-05-15 | 2014-05-16 | 2014-05-17 | 2014-05-18 | 2014-05-19 | 2014-05-20 | 2014-05-21 | 2014-05-22 | 2014-05-23 | 2014-05-24 | 2014-05-25 | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-01 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07 | 2014-06-08
11.3 | 1 | 1 | Project Start | 11.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
10.3 | 2 | 2 | Client Meeeting 1 | #N/A | #N/A | #N/A | #N/A | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
9.3 | 3 | 3 | Requirement Integration | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.3 | 9.3 | 9.3 | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
8.3 | 4 | 4 | Project Timeline Compilation | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
7.3 | 5 | 5 | First Demo Session | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
6.3 | 6 | 6 | Requirement Re-do | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3 | 6.3
5.3 | 7 | 7 | System Prototype & DB Design | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3 | 5.3
4.3 | 8 | 8 | Progress Report 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
3.3 | 9 | 9 | Meet Stacey 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | #N/A | #N/A
|  |  |  | 2014-05-09 | 2014-05-10 | 2014-05-11 | 2014-05-12 | 2014-05-13 | 2014-05-14 | 2014-05-15 | 2014-05-16 | 2014-05-17 | 2014-05-18 | 2014-05-19 | 2014-05-20 | 2014-05-21 | 2014-05-22 | 2014-05-23 | 2014-05-24 | 2014-05-25 | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-01 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07
|  | 1 | PROJECT START | 11.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 2 | CLIENT MEEETING 1 | #N/A | #N/A | #N/A | #N/A | 10.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 3 | REQUIREMENT INTEGRATION | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 4 | PROJECT TIMELINE COMPILATION | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 5 | FIRST DEMO SESSION | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 6 | REQUIREMENT RE-DO | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 7 | SYSTEM PROTOTYPE & DB DESIGN | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 8 | PROGRESS REPORT 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.3 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | 9 | MEET STACEY 1 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.3 | #N/A
|  |  |  | 2014-05-09 | 2014-05-10 | 2014-05-11 | 2014-05-12 | 2014-05-13 | 2014-05-14 | 2014-05-15 | 2014-05-16 | 2014-05-17 | 2014-05-18 | 2014-05-19 | 2014-05-20 | 2014-05-21 | 2014-05-22 | 2014-05-23 | 2014-05-24 | 2014-05-25 | 2014-05-26 | 2014-05-27 | 2014-05-28 | 2014-05-29 | 2014-05-30 | 2014-05-31 | 2014-06-01 | 2014-06-02 | 2014-06-03 | 2014-06-04 | 2014-06-05 | 2014-06-06 | 2014-06-07
|  |  | Current Day | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2014-05-01 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | May 2014 - Top Band | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2014-06-01 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
|  |  | Jun 2014 - Top Band | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13 | 13 | 13 | 13 | 13 | 13 | 13
|  |  | 2014-05-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  | 2014-06-02 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5 | #N/A | #N/A | #N/A | #N/A | #N/A
|  |  |  | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
|  |  | 3 | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT
|  |  |  | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3
|  |  |  | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07